## Staff
Staff | Amount | Gross Annual Salary | Annual Salary Cost | TOTAL
Project Manager | 1 | 42000 | 54600 | 54600
Lead Researcher | 1 | 42000 | 54600 | 54600
Software Engineer | 1 | 32000 | 41600 | 41600
Junior Researcher | 1 | 25000 | 32500 | 32500
Junior Researcher II | 1 | 25000 | 32500 | 32500
TOTAL | 5 |  |  | 215800

## Staff Productivity
Staff | TOTAL | Prod (%) | Direct Cost | IC(%) | Indirect Cost
Project Manager | 54600 | 0% | 0 | 100% | 54600
Lead Researcher | 54600 | 70% | 38220 | 30% | 16380
Software Engineer | 41600 | 80% | 33280 | 20% | 8320
Junior Researcher | 32500 | 80% | 26000 | 20% | 6500
Junior Researcher II | 32500 | 80% | 26000 | 20% | 6500
TOTAL | 215800 |  | 123500 |  | 92300

## Indirect Costs
Service | Monthly Cost | Yearly Cost
Cleaning | 20 | 240
Light Consumption | 70 | 840
Water Consumption | 20 | 240
Heating | 20 | 240
Internet provider | 65.99 | 791.88
Movility Costs | 40 | 480
Total |  | 2831.88

## Production Costs
License/Team | Units | Price | Total Price | Annual Cost | Type | Term
Tobii pro nano | 1 | 2500 | 2500 | 208.3333 | Amortization | -
Tobii pro lab license | 1 | 1800 | 1800 | 150 | Amortization | -
Total |  |  |  | 358.3333

## Billing Needs
Indirect plus direct costs | 218990.2133
Desired Benefit | 54747.5533 | Desired Benefit | 25%
Billing Needs | 273737.7667

## Schedule
Staff | Prod(%) | Hours / year | Productive hours / year (per person) | Productive Hours (Total)
Project Manager | 0% | 1784 | 0 | 0
Lead Researcher | 70% | 1784 | 1248.8 | 1248.8
Software Engineer | 80% | 1784 | 1427.2 | 1427.2
Junior Researcher | 80% | 1784 | 1427.2 | 1427.2
Junior Researcher II | 80% | 1784 | 1427.2 | 1427.2
Total |  |  |  | 5530.4

## Price per Hour
| Staff | Price / hour | Price /hour with no benefit | Productive Hours | Billing
| Project Manager | 0 | 0 | 0 | 0
| Lead Researcher | 70 | 56 | 1248.8 | 87416
| Software Engineer | 50 | 40 | 1427.2 | 71360
| Junior Researcher | 41.25 | 33 | 1427.2 | 58872
| Junior Researcher II | 41.25 | 33 | 1427.2 | 58872
| Total |  |  |  | 276520
| Indirect | Means | Non productive
| 2831.88 | 358.3333 | 54600
Notes to calc | 707.97 | 89.5833 | 13650 | 14447.5533

## Summary
Concept
Total direct costs | 123500
Total Indirect Costs | 95490.2133
Sum of both direct and indirect costs | 218990.2133
Desired Benefit | 54747.5533
Total Cost (Sum of costs + benefit) | 273737.7667
Possible billing by productivity hours and price per hour | 276520
Total cost and billing costs margin | 1.016%

## Budget
Code | Number | Part | Total
1 |  | Previous Planning and State of the art | 6622.5
| 1 | Previous Planning | 1005
| 2 | State of the Art | 5617.5
2 |  | Experiment | 13588.75 | 23991.5747
| 1 | Experiment Proposal | 2943.75 | 5197.3285
| 2 | Experiment Development | 2722.5 | 4806.7013
| 3 | Data analysis | 7922.5 | 13987.5449
3 |  | Documentation for the paper | 3041.25 | 5369.4693
|  | Total | 23252.5 | 29361.044
|  | Total con beneficios | 29065.625
|  | Contingencia | 295.419
|  | Beneficio total | 6108.544
|  | Porcentaje de Reparticion al Cliente | 0.76555

## Client
Code | Number | Part | Total
1 |  | Experiment | 23991.5747
| 1 | Experiment Proposal | 5197.3285
| 2 | Experiment Development | 4806.7013
| 3 | Data analysis | 13987.5449
2 |  | Documentation for the paper | 5369.4693
Total |  |  | 29361.044

## Part 1
Index 1 | Index 2 | Index 3 | Index 4 | Task Name | Quantity | Units | Price | Subtotal(3) | Subtotal (2) | Subtotal(1) | Total
001 |  |  |  | Previous Planning | [6 empty] | 1005
| 001 |  |  | Research Process Planning | [5 empty] | 0
|  | 001 |  | Needs Analysis |  |  |  |  | 0
|  |  | 001 | Project Manager | 6 | Hours | 0 | 0
|  | 002 |  | Organization and definition of roles
|  |  | 001 | Project Manager | 3 | Hours | 0 | 0
| 002 |  |  | Definition of technology needs | [5 empty] | 1005
|  | 001 |  | Identification of technology needs |  |  |  |  | 210
|  |  | 001 | Lead Researcher | 3 | Hours | 70 | 210
|  | 002 |  | Selection of tools and technologies |  |  |  |  | 720
|  |  | 001 | Lead Researcher | 6 | Hours | 70 | 420
|  |  | 002 | Software Engineer | 6 | Hours | 50 | 300
|  | 003 |  | Acquisition of chosen technologies |  |  |  |  | 75
|  |  | 001 | Software Engineer | 1.5 | Hours | 50 | 75
| 003 |  |  | Project Planning | [5 empty] | 0
|  | 001 |  | OBS |  |  |  |  | 0
|  |  | 001 | Project Manager | 3 | Hours | 0 | 0
|  | 002 |  | WBS |  |  |  |  | 0
|  |  | 001 | Project Manager | 18 | Hours | 0 | 0
|  | 003 |  | Risk Management |  |  |  |  | 0
|  |  | 001 | Project Manager | 18 | Hours | 0 | 0
|  | 004 |  | Budget Creation |  |  |  |  | 0
|  |  | 001 | Project Manager | 18 | Hours | 0 | 0
002 |  |  |  | State of the art | [6 empty] | 5617.5
| 001 |  |  | Search and analysis | [5 empty] | 2722.5
|  | 001 |  | Junior Researcher 1 | 33 | Hours | 41.25 |  | 1361.25
|  | 002 |  | Junior Researcher 2 | 33 | Hours | 41.25 |  | 1361.25
| 002 |  |  | First Bake | [5 empty] | 1237.5
|  | 001 |  | Junior Researcher 1 | 15 | Hours | 41.25 |  | 618.75
|  | 002 |  | Junior Researcher 2 | 15 | Hours | 41.25 |  | 618.75
| 003 |  |  | Second and final bake | [5 empty] | 1237.5
|  | 001 |  | Junior Researcher 1 | 15 | Hours | 41.25 |  | 618.75
|  | 002 |  | Junior Researcher 2 | 15 | Hours | 41.25 |  | 618.75
| 004 |  |  | Final Presentation | [5 empty] | 420
|  | 001 |  | Lead Researcher | 6 | Hours | 70 |  | 420
TOTAL | [10 empty] | 6622.5

## Part 2
Index 1 | Index 2 | Index 3 | Index 4 | Task Name | Quantity | Units | Price | Subtotal(3) | Subtotal (2) | Subtotal(1) | Total
001 |  |  |  | Experiment Proposal | [6 empty] | 2943.75
| 001 |  |  | In depth experiment creation | [5 empty] | 2100
|  | 001 |  | Lead Researcher | 30 | Hours | 70 |  | 2100
| 002 |  |  | Webpage selection | [5 empty] | 300
|  | 001 |  | Software Engineer | 6 | Hours | 50 |  | 300
| 003 |  |  | Creation of the form | [5 empty] | 123.75
|  | 001 |  | Junior Researcher 2 | 3 | Hours | 41.25 |  | 123.75
| 004 |  |  | Tobii pro lab configuration | [5 empty] | 420
|  | 001 |  | Lead Researcher | 6 | Hours | 70 |  | 420
002 |  |  |  | Experiment Development | [6 empty] | 2722.5
| 001 |  |  | Book the desired place | [5 empty] | 247.5
|  | 001 |  | Junior Researcher 1 | 6 | Hours | 41.25 |  | 247.5
| 002 |  |  | Preparation of material | [5 empty] | 247.5
|  | 001 |  | Junior Researcher 2 | 6 | Hours | 41.25 |  | 247.5
| 003 |  |  | Data Retrieval | [5 empty] | 2475
|  | 001 |  | Junior Researcher 1 | 30 | Hours | 41.25 |  | 1237.5
|  | 002 |  | Junior Researcher 2 | 30 | Hours | 41.25 |  | 1237.5
003 |  |  |  | Data analysis | [6 empty] | 7922.5
| 001 |  |  | Data preprocessing | [5 empty] | 2190
|  | 001 |  | Tobii pro lab AOI creation |  |  |  |  | 990
|  |  | 001 | Junior Researcher 1 | 24 | Hours | 41.25 | 990
|  | 002 |  | Data Download |  |  |  |  | 300
|  |  | 001 | Software Engineer | 6 | Hours | 50 | 300
|  | 003 |  | Preprocessing implementation |  |  |  |  | 900
|  |  | 001 | Software Engineer | 18 | Hours | 50 | 900
| 002 |  |  | Data processing | [5 empty] | 1800
|  | 001 |  | Software Engineer | 36 | Hours | 50 |  | 1800
| 003 |  |  | Statistical Study | [5 empty] | 1680
|  | 001 |  | Lead Researcher | 24 | Hours | 70 |  | 1680
| 004 |  |  | Collect conclussions and results | [5 empty] | 2100
|  | 001 |  | Lead Researcher | 30 | Hours | 70 |  | 2100
| 005 |  |  | Final meeting | [5 empty] | 152.5
|  | 001 |  | Junior Researcher 1 | 1 | Hours | 41.25 |  | 41.25
|  | 002 |  | Junior Researcher 2 | 1 | Hours | 41.25 |  | 41.25
|  | 003 |  | Lead Researcher | 1 | Hours | 70 |  | 70
TOTAL | [10 empty] | 13588.75

## Part 3
Index 1 | Index 2 | Index 3 | Task Name | Quantity | Units | Price | Subtotal (2) | Subtotal(1) | Total
001 |  |  | Documentation | [5 empty] | 3041.25
| 001 |  | Abstract Writing |  |  |  |  | 123.75
|  | 001 | Junior Researcher 1 | 3 | Hours | 41.25 | 123.75
| 002 |  | Introduction Writing |  |  |  |  | 123.75
|  | 001 | Junior Researcher 2 | 3 | Hours | 41.25 | 123.75
| 003 |  | Literature Writing |  |  |  |  | 123.75
|  | 001 | Junior Researcher 1 | 3 | Hours | 41.25 | 123.75
| 004 |  | Method Writing |  |  |  |  | 247.5
|  | 001 | Junior Researcher 2 | 6 | Hours | 41.25 | 247.5
| 005 |  | Results and discussion writing |  |  |  |  | 495
|  | 001 | Junior Researcher 1 | 12 | Hours | 41.25 | 495
| 006 |  | Conclusion Writing |  |  |  |  | 247.5
|  | 001 | Junior Researcher 2 | 6 | Hours | 41.25 | 247.5
| 007 |  | Reference review |  |  |  |  | 420
|  | 001 | Lead Researcher | 6 | Hours | 70 | 420
| 008 |  | Final documentation review |  |  |  |  | 1260
|  | 002 | Lead Researcher | 18 | Hours | 70 | 1260
TOTAL | [8 empty] | 3041.25